## TASK
task_code | wbs_id | task_name | target_drtn_hr_cnt | start_date | end_date | remain_drtn_hr_cnt | pred_list | succ_list | total_float_hr_cnt | status_code
Activity ID | WBS Code | Activity Name | Original Duration(d) | (*)Start | (*)Finish | Remaining Duration(d) | (*)Predecessors | (*)Successors | (*)Total Float(d) | Activity Status
A1100 | SEPID-0014.PIP-AGF.CS.UN | CS Pipe & Fitting Under 2" - Mobilization | 1 | 2026-01-06 08:00 | 2026-01-06 17:00 | 1 | A2041 | A1110 | 10 | Not Started
A1110 | SEPID-0014.PIP-AGF.CS.UN | CS Pipe & Fitting Under 2" - Material Handling | 252 | 2026-01-07 08:00 | 2026-09-15 17:00 | 252 | A1100 | A1120 | 10 | Not Started
A1120 | SEPID-0014.PIP-AGF.CS.UN | CS Pipe & Fitting Under 2" - Fit-up | 252 | 2026-01-08 08:00 | 2026-09-16 17:00 | 252 | A1110 | A1130, A1140 | 10 | Not Started
A1130 | SEPID-0014.PIP-AGF.CS.UN | CS Pipe & Fitting Under 2" - Welding | 252 | 2026-01-09 08:00 | 2026-09-17 17:00 | 252 | A1120 |  | 11 | Not Started
A1140 | SEPID-0014.PIP-AGF.CS.UN | CS Pipe & Fitting Under 2" - (QC & QA Report ) | 254 | 2026-01-08 08:00 | 2026-09-18 17:00 | 254 | A1120 |  | 10 | Not Started
A1150 | SEPID-0014.PIP-AGF.CS.AB | CS Pipe & Fitting Above 2" - Mobilization | 1 | 2025-05-27 08:00 | 2025-05-27 17:00 | 1 | A2041 | A1160 | 60 | Not Started
A1160 | SEPID-0014.PIP-AGF.CS.AB | CS Pipe & Fitting Above 2" - Material Handling | 426 | 2025-05-28 08:00 | 2026-07-27 17:00 | 426 | A1150 | A1170 | 60 | Not Started
A1170 | SEPID-0014.PIP-AGF.CS.AB | CS Pipe & Fitting Above 2" - Fit-up | 426 | 2025-05-29 08:00 | 2026-07-28 17:00 | 426 | A1160 | A1180, A1190 | 60 | Not Started
A1180 | SEPID-0014.PIP-AGF.CS.AB | CS Pipe & Fitting Above 2" - Welding | 426 | 2025-05-30 08:00 | 2026-07-29 17:00 | 426 | A1170 | A1400 | 61 | Not Started
A1190 | SEPID-0014.PIP-AGF.CS.AB | CS Pipe & Fitting Above 2" - (QC & QA Report ) | 428 | 2025-05-29 08:00 | 2026-07-30 17:00 | 428 | A1170 |  | 60 | Not Started
A1200 | SEPID-0014.PIP-AGF.SAM.SS | SS Pipe & Fitting & Flange Pipe & Fitting - Mobilization | 1 | 2025-09-02 08:00 | 2025-09-02 17:00 | 1 | A2041 | A1210 | 10 | Not Started
A1210 | SEPID-0014.PIP-AGF.SAM.SS | SS Pipe & Fitting & Flange Pipe & Fitting - Material Handling | 378 | 2025-09-03 08:00 | 2026-09-15 17:00 | 378 | A1200 | A1220 | 10 | Not Started
A1220 | SEPID-0014.PIP-AGF.SAM.SS | SS Pipe & Fitting & Flange Pipe & Fitting - Fit-up | 378 | 2025-09-04 08:00 | 2026-09-16 17:00 | 378 | A1210 | A1230, A1240 | 10 | Not Started
A1230 | SEPID-0014.PIP-AGF.SAM.SS | SS Pipe & Fitting & Flange Pipe & Fitting - Welding | 378 | 2025-09-05 08:00 | 2026-09-17 17:00 | 378 | A1220 |  | 11 | Not Started
A1240 | SEPID-0014.PIP-AGF.SAM.SS | SS Pipe & Fitting & Flange Pipe & Fitting - (QC & QA Report ) | 380 | 2025-09-04 08:00 | 2026-09-18 17:00 | 380 | A1220 |  | 10 | Not Started
A1250 | SEPID-0014.PIP-AGF.SAM.AS | AS Pipe & Fitting - Mobilization | 1 | 2025-08-05 08:00 | 2025-08-05 17:00 | 1 | A2041 | A1260 | 10 | Not Started
A1260 | SEPID-0014.PIP-AGF.SAM.AS | AS Pipe & Fitting - Material Handling | 406 | 2025-08-06 08:00 | 2026-09-15 17:00 | 406 | A1250 | A1270 | 10 | Not Started
A1270 | SEPID-0014.PIP-AGF.SAM.AS | AS Pipe & Fitting - Fit-up | 406 | 2025-08-07 08:00 | 2026-09-16 17:00 | 406 | A1260 | A1280, A1290 | 10 | Not Started
A1280 | SEPID-0014.PIP-AGF.SAM.AS | AS Pipe & Fitting - Welding | 406 | 2025-08-08 08:00 | 2026-09-17 17:00 | 406 | A1270 |  | 11 | Not Started
A1290 | SEPID-0014.PIP-AGF.SAM.AS | AS Pipe & Fitting - (QC & QA Report ) | 408 | 2025-08-07 08:00 | 2026-09-18 17:00 | 408 | A1270 |  | 10 | Not Started
A1310 | SEPID-0014.PIP-AGF.SAM.MO | Monel Pipe & Fitting - Mobilization | 1 | 2026-04-28 08:00 | 2026-04-28 17:00 | 1 | A2041 | A1320 | 3 | Not Started
A1320 | SEPID-0014.PIP-AGF.SAM.MO | Monel Pipe & Fitting - Material Handling | 147 | 2026-04-29 08:00 | 2026-09-22 17:00 | 147 | A1310 | A1330 | 3 | Not Started
A1330 | SEPID-0014.PIP-AGF.SAM.MO | Monel Pipe & Fitting - Fit-up | 147 | 2026-04-30 08:00 | 2026-09-23 17:00 | 147 | A1320 | A1340, A1350 | 3 | Not Started
A1340 | SEPID-0014.PIP-AGF.SAM.MO | Monel Pipe & Fitting - Welding | 147 | 2026-05-01 08:00 | 2026-09-24 17:00 | 147 | A1330 |  | 4 | Not Started
A1350 | SEPID-0014.PIP-AGF.SAM.MO | Monel Pipe & Fitting - (QC & QA Report ) | 149 | 2026-04-30 08:00 | 2026-09-25 17:00 | 149 | A1330 |  | 3 | Not Started
A1360 | SEPID-0014.PIP-AGF.GAL.1 | GAL Pipe & Fitting & Flange Mobilization | 1 | 2025-12-16 08:00 | 2025-12-16 17:00 | 1 | A2041 | A1370 | 11 | Not Started
A1370 | SEPID-0014.PIP-AGF.GAL.1 | GAL Pipe & Fitting & Flange Material Handling | 273 | 2025-12-17 08:00 | 2026-09-15 17:00 | 273 | A1360 | A1380 | 11 | Not Started
A1380 | SEPID-0014.PIP-AGF.GAL.1 | GAL Pipe & Fitting & Flange Installation & Thread | 273 | 2025-12-18 08:00 | 2026-09-16 17:00 | 273 | A1370 | A1390 | 11 | Not Started
A1390 | SEPID-0014.PIP-AGF.GAL.1 | GAL Pipe & Fitting & Flange - (QC & QA Report ) | 274 | 2025-12-18 08:00 | 2026-09-17 17:00 | 274 | A1380 |  | 11 | Not Started
A1400 | SEPID-0014.VAL.INST | Valve Installation - Mobilization | 1 | 2025-05-27 08:00 | 2025-05-27 17:00 | 1 | A1180 | A1410 | 236 | Not Started
A1410 | SEPID-0014.VAL.INST | Valve Installation - Handling | 252 | 2025-05-28 08:00 | 2026-02-03 17:00 | 252 | A1400 | A1420 | 236 | Not Started
A1420 | SEPID-0014.VAL.INST | Valve Installation - Installation | 252 | 2025-05-29 08:00 | 2026-02-04 17:00 | 252 | A1410 | A1430 | 236 | Not Started
A1430 | SEPID-0014.VAL.INST | Valve Installation - (QC & QA Report ) | 252 | 2025-05-29 08:00 | 2026-02-04 17:00 | 252 | A1420 |  | 236 | Not Started
A1440 | SEPID-0014.VAL.SI | Special Items - Mobilization | 1 | 2025-05-27 08:00 | 2025-05-27 17:00 | 1 |  | A1450 | 341 | Not Started
A1450 | SEPID-0014.VAL.SI | Special Items - Handling | 147 | 2025-05-28 08:00 | 2025-10-21 17:00 | 147 | A1440 | A1460 | 341 | Not Started
A1460 | SEPID-0014.VAL.SI | Special Items - Installation | 147 | 2025-05-29 08:00 | 2025-10-22 17:00 | 147 | A1450 | A1470 | 341 | Not Started
A1470 | SEPID-0014.VAL.SI | Special Items - (QC & QA Report ) | 147 | 2025-05-29 08:00 | 2025-10-22 17:00 | 147 | A1460 |  | 341 | Not Started
A1480 | SEPID-0014.SUP.NOR | Pipe Support Mobilization | 1 | 2025-05-27 08:00 | 2025-05-27 17:00 | 1 |  | A1490 | 47 | Not Started
A1490 | SEPID-0014.SUP.NOR | Pipe Support Material Supply | 420 | 2025-05-28 08:00 | 2026-07-21 17:00 | 420 | A1480 | A1500, A2000 | 47 | Not Started
A1500 | SEPID-0014.SUP.NOR | Pipe Support Fabrication | 420 | 2025-05-29 08:00 | 2026-07-22 17:00 | 420 | A1490 | A1510, A1540 | 47 | Not Started
A1510 | SEPID-0014.SUP.NOR | Pipe Support Sandblast & Primer | 420 | 2025-06-05 08:00 | 2026-07-29 17:00 | 420 | A1500 | A1520 | 47 | Not Started
A1520 | SEPID-0014.SUP.NOR | Pipe Support Painting | 420 | 2025-06-12 08:00 | 2026-08-05 17:00 | 420 | A1510 | A1530 | 47 | Not Started
A1530 | SEPID-0014.SUP.NOR | Pipe Support Installation | 420 | 2025-06-19 08:00 | 2026-08-12 17:00 | 420 | A1520 |  | 47 | Not Started
A1540 | SEPID-0014.SUP.NOR | Pipe Support - (QC & QA Report ) | 420 | 2025-05-29 08:00 | 2026-07-22 17:00 | 420 | A1500 |  | 68 | Not Started
A1550 | SEPID-0014.SUP.SPL | Special Pipe Support Mobilization | 1 | 2025-05-27 08:00 | 2025-05-27 17:00 | 1 |  | A1560 | 340 | Not Started
A1560 | SEPID-0014.SUP.SPL | Special Pipe Support Material Handling | 147 | 2025-05-28 08:00 | 2025-10-21 17:00 | 147 | A1550 | A1570 | 340 | Not Started
A1570 | SEPID-0014.SUP.SPL | Special Pipe Support Installation | 147 | 2025-05-29 08:00 | 2025-10-22 17:00 | 147 | A1560 | A1580 | 340 | Not Started
A1580 | SEPID-0014.SUP.SPL | Special Pipe Support - (QC & QA Report ) | 147 | 2025-05-30 08:00 | 2025-10-23 17:00 | 147 | A1570 |  | 340 | Not Started
A1590 | SEPID-0014.INS.PNT | Painting (Pipe & Fittings) Mobilization | 1 | 2025-05-27 08:00 | 2025-05-27 17:00 | 1 |  | A1600 | 0 | Not Started
A1600 | SEPID-0014.INS.PNT | Painting (Pipe & Fittings) Surface Preparation (Sand / Grit Blast) | 390 | 2025-05-28 08:00 | 2026-06-21 17:00 | 390 | A1590 | A1610, A1670 | 0 | Not Started
A1610 | SEPID-0014.INS.PNT | Painting (Pipe & Fittings) Primer Painting | 390 | 2025-06-04 08:00 | 2026-06-28 17:00 | 390 | A1600 | A1620 | 1 | Not Started
A1620 | SEPID-0014.INS.PNT | Painting (Pipe & Fittings) Intermediate Painting | 175 | 2026-03-09 08:00 | 2026-08-30 17:00 | 175 | A1610 | A1630 | 1 | Not Started
A1630 | SEPID-0014.INS.PNT | Painting (Pipe & Fittings) Top Coat Painting | 175 | 2026-03-16 08:00 | 2026-09-06 17:00 | 175 | A1620 | A1640 | 1 | Not Started
A1640 | SEPID-0014.INS.PNT | Painting (Pipe & Fittings) Color Coding ,Lettering & Marking | 175 | 2026-03-23 08:00 | 2026-09-13 17:00 | 175 | A1630 | A1650 | 1 | Not Started
A1650 | SEPID-0014.INS.PNT | Painting (Pipe & Fittings) Tie Coat Paint layer On Piping | 175 | 2026-03-30 08:00 | 2026-09-20 17:00 | 175 | A1640 | A1660 | 1 | Not Started
A1660 | SEPID-0014.INS.PNT | Painting (Pipe & Fittings) Tie Coat Paint layer On Supports | 175 | 2026-04-06 08:00 | 2026-09-27 17:00 | 175 | A1650 |  | 1 | Not Started
A1670 | SEPID-0014.INS.PNT | Painting (Pipe & Fittings) - (QC & QA Report ) | 489 | 2025-05-28 08:00 | 2026-09-28 17:00 | 489 | A1600 |  | 0 | Not Started
A1680 | SEPID-0014.INS.HOT.PF | Insulation Pipe & Fitting Mobilization | 1 | 2025-05-27 08:00 | 2025-05-27 17:00 | 1 |  | A1690 | 244 | Not Started
A1690 | SEPID-0014.INS.HOT.PF | Insulation Pipe & Fitting Material Handling | 231 | 2025-05-28 08:00 | 2026-01-13 17:00 | 231 | A1680 | A1700 | 244 | Not Started
A1700 | SEPID-0014.INS.HOT.PF | Insulation Pipe & Fitting Cutting & Shaping | 231 | 2025-05-28 08:00 | 2026-01-13 17:00 | 231 | A1690 | A1710, A1730 | 244 | Not Started
A1710 | SEPID-0014.INS.HOT.PF | Insulation Pipe & Fitting Erection Of Insulation | 231 | 2025-06-04 08:00 | 2026-01-20 17:00 | 231 | A1700 | A1720 | 244 | Not Started
A1720 | SEPID-0014.INS.HOT.PF | Insulation Pipe & Fitting Sheeting & Sealing | 231 | 2025-06-11 08:00 | 2026-01-27 17:00 | 231 | A1710 |  | 244 | Not Started
A1730 | SEPID-0014.INS.HOT.PF | Insulation Pipe & Fitting Sheeting & Sealing - (QC & QA Report ) | 245 | 2025-05-28 08:00 | 2026-01-27 17:00 | 245 | A1700 |  | 244 | Not Started
A1740 | SEPID-0014.INS.HOT.VA | Insulation Valve & Flange Mobilization | 1 | 2025-05-27 08:00 | 2025-05-27 17:00 | 1 |  | A1750 | 286 | Not Started
A1750 | SEPID-0014.INS.HOT.VA | Insulation Valve & Flange Material Handling | 203 | 2025-05-28 08:00 | 2025-12-16 17:00 | 203 | A1740 | A1760 | 286 | Not Started
A1760 | SEPID-0014.INS.HOT.VA | Insulation Valve & Flange Cutting & Shaping | 203 | 2025-05-28 08:00 | 2025-12-16 17:00 | 203 | A1750 | A1770 | 286 | Not Started
A1770 | SEPID-0014.INS.HOT.VA | Insulation Valve & Flange Erection Of Insulation | 203 | 2025-05-28 08:00 | 2025-12-16 17:00 | 203 | A1760 | A1780 | 286 | Not Started
A1780 | SEPID-0014.INS.HOT.VA | Insulation Valve & Flange Sheeting & Sealing | 203 | 2025-05-28 08:00 | 2025-12-16 17:00 | 203 | A1770 | A1790 | 286 | Not Started
A1790 | SEPID-0014.INS.HOT.VA | Insulation Valve & Flange Sheeting & Sealing - (QC & QA Report ) | 203 | 2025-05-28 08:00 | 2025-12-16 17:00 | 203 | A1780 |  | 286 | Not Started
A1800 | SEPID-0014.TPC.NDT | Non-Destructive Testing-NDT Mobilization | 1 | 2025-05-27 08:00 | 2025-05-27 17:00 | 1 |  |  | 489 | Not Started
A1810 | SEPID-0014.TPC.NDT | Radiographic Testing - RT | 469 | 2025-05-27 08:00 | 2026-09-07 17:00 | 469 |  |  | 21 | Not Started
A1820 | SEPID-0014.TPC.NDT | Ultrasonic Testing - UT | 469 | 2025-05-27 08:00 | 2026-09-07 17:00 | 469 |  |  | 21 | Not Started
A1830 | SEPID-0014.TPC.NDT | Penetrant Testing - PT | 469 | 2025-05-27 08:00 | 2026-09-07 17:00 | 469 |  |  | 21 | Not Started
A1840 | SEPID-0014.TPC.NDT | Magnetic Particle Testing - MT | 469 | 2025-05-27 08:00 | 2026-09-07 17:00 | 469 |  |  | 21 | Not Started
A1850 | SEPID-0014.TPC.NDT | NDT - (QC & QA Report ) | 469 | 2025-05-27 08:00 | 2026-09-07 17:00 | 469 |  |  | 21 | Not Started
A1860 | SEPID-0014.TPC.PWHT | PWHT Mobilization | 1 | 2025-05-27 08:00 | 2025-05-27 17:00 | 1 |  | A1870 | 104 | Not Started
A1870 | SEPID-0014.TPC.PWHT | PWHT | 385 | 2025-05-28 08:00 | 2026-06-16 17:00 | 385 | A1860 | A1880 | 104 | Not Started
A1880 | SEPID-0014.TPC.PWHT | PWHT - (QC & QA Report ) | 385 | 2025-05-28 08:00 | 2026-06-16 17:00 | 385 | A1870 |  | 104 | Not Started
A1890 | SEPID-0014.TPC.PRE | Preparation of Test Package | 329 | 2025-05-27 08:00 | 2026-04-20 17:00 | 329 |  | A1900 | 160 | Not Started
A1900 | SEPID-0014.TPC.PRE | Precommissining of Metalic Piping - Mobilization | 1 | 2025-05-27 08:00 | 2025-05-27 17:00 | 1 | A1890 | A1910 | 160 | Not Started
A1910 | SEPID-0014.TPC.PRE | Line Check | 329 | 2025-05-28 08:00 | 2026-04-21 17:00 | 329 | A1900 | A1920 | 160 | Not Started
A1920 | SEPID-0014.TPC.PRE | Hydro Test | 245 | 2025-05-28 08:00 | 2026-01-27 17:00 | 245 | A1910 | A1930 | 244 | Not Started
A1930 | SEPID-0014.TPC.PRE | Cleaning & Flushing & Drying | 245 | 2025-05-28 08:00 | 2026-01-27 17:00 | 245 | A1920 | A1940 | 244 | Not Started
A1940 | SEPID-0014.TPC.PRE | Reinstatement | 245 | 2025-05-28 08:00 | 2026-01-27 17:00 | 245 | A1930 | A1950 | 244 | Not Started
A1950 | SEPID-0014.TPC.PRE | Precommissining of Metalic Piping - (QC & QA Report ) | 245 | 2025-05-28 08:00 | 2026-01-27 17:00 | 245 | A1940 |  | 244 | Not Started
A1960 | SEPID-0014.TPC.CHM | Chemical Clearing (Acid & Alkaline) Mobilization | 1 | 2025-05-27 08:00 | 2025-05-27 17:00 | 1 |  | A1970 | 385 | Not Started
A1970 | SEPID-0014.TPC.CHM | Chemical Clearing (Acid & Alkaline) Material Supply | 105 | 2025-05-27 08:00 | 2025-09-08 17:00 | 105 | A1960 | A1980 | 385 | Not Started
A1980 | SEPID-0014.TPC.CHM | Chemical Clearing (Acid & Alkaline) | 105 | 2025-05-27 08:00 | 2025-09-08 17:00 | 105 | A1970 | A1990 | 385 | Not Started
A1990 | SEPID-0014.TPC.CHM | Chemical Clearing (Acid & Alkaline) - (QC & QA Report ) | 105 | 2025-05-27 08:00 | 2025-09-08 17:00 | 105 | A1980 |  | 385 | Not Started
A2000 | SEPID-0014.TPC.PMI | P.M.I - Mobilization | 1 | 2025-05-28 08:00 | 2025-05-28 17:00 | 1 | A1490 | A2010 | 69 | Not Started
A2010 | SEPID-0014.TPC.PMI | P.M.I | 420 | 2025-05-28 08:00 | 2026-07-21 17:00 | 420 | A2000 | A2020 | 69 | Not Started
A2020 | SEPID-0014.TPC.PMI | P.M.I - (QC & QA Report ) | 420 | 2025-05-28 08:00 | 2026-07-21 17:00 | 420 | A2010 |  | 69 | Not Started
A2030 | SEPID-0014.Ml | Project Start Date | 0 | 2025-05-27 08:00 |  | 0 |  | A2033 | 3 | Not Started
A2060 | SEPID-0014.Ml | Project Finish Date | 0 |  | 2025-05-27 08:00 | 0 |  |  | 490 | Not Started
A2035 | SEPID-0014.Ml | Project Effective Date | 0 | 2025-05-27 08:00 |  | 0 | A2033 | A2041 | 3 | Not Started
A2041 | SEPID-0014.Ml | Project Kickoff Meeting | 0 | 2025-05-27 08:00 |  | 0 | A2035 | A1150, A1100, A1200, A1250, A1310, A1360 | 3 | Not Started
A2033 | SEPID-0014.Ml | Project Land Delivery | 0 | 2025-05-27 08:00 |  | 0 | A2030 | A2035 | 3 | Not Started

## TASKPRED
pred_task_id | task_id | pred_type | PREDTASK__status_code | TASK__status_code | pred_proj_id | proj_id | predtask__projwbs__wbs_full_name | task__projwbs__wbs_full_name | predtask__task_name | task__task_name | lag_hr_cnt | predtask__rsrc_id | task__rsrc_id | delete_record_flag
Predecessor | Successor | Relationship Type | (*)Predecessor Activity Status | (*)Successor Activity Status | (*)Predecessor Project | (*)Successor Project | (*)Predecessor WBS | (*)Successor WBS | (*)Predecessor Activity Name | (*)Successor Activity Name | Lag(d) | (*)Predecessor Primary Resource | (*)Successor Primary Resource | Delete This Row
A2035 | A2041 | FS | Not Started | Not Started | SEPID-0014 | SEPID-0014 | SEPID-0014.Ml Mileston Important | SEPID-0014.Ml Mileston Important | Project Effective Date | Project Kickoff Meeting | 0
A2030 | A2033 | FS | Not Started | Not Started | SEPID-0014 | SEPID-0014 | SEPID-0014.Ml Mileston Important | SEPID-0014.Ml Mileston Important | Project Start Date | Project Land Delivery | 0
A2033 | A2035 | FS | Not Started | Not Started | SEPID-0014 | SEPID-0014 | SEPID-0014.Ml Mileston Important | SEPID-0014.Ml Mileston Important | Project Land Delivery | Project Effective Date | 0
A1100 | A1110 | FS | Not Started | Not Started | SEPID-0014 | SEPID-0014 | SEPID-0014.PIP-AGF.CS.UN CS Pipe & Fitting Under 2" | SEPID-0014.PIP-AGF.CS.UN CS Pipe & Fitting Under 2" | CS Pipe & Fitting Under 2" - Mobilization | CS Pipe & Fitting Under 2" - Material Handling | 0
A1110 | A1120 | SS | Not Started | Not Started | SEPID-0014 | SEPID-0014 | SEPID-0014.PIP-AGF.CS.UN CS Pipe & Fitting Under 2" | SEPID-0014.PIP-AGF.CS.UN CS Pipe & Fitting Under 2" | CS Pipe & Fitting Under 2" - Material Handling | CS Pipe & Fitting Under 2" - Fit-up | 1
A1120 | A1130 | SS | Not Started | Not Started | SEPID-0014 | SEPID-0014 | SEPID-0014.PIP-AGF.CS.UN CS Pipe & Fitting Under 2" | SEPID-0014.PIP-AGF.CS.UN CS Pipe & Fitting Under 2" | CS Pipe & Fitting Under 2" - Fit-up | CS Pipe & Fitting Under 2" - Welding | 1
A1150 | A1160 | FS | Not Started | Not Started | SEPID-0014 | SEPID-0014 | SEPID-0014.PIP-AGF.CS.AB CS Pipe & Fitting Above 2" | SEPID-0014.PIP-AGF.CS.AB CS Pipe & Fitting Above 2" | CS Pipe & Fitting Above 2" - Mobilization | CS Pipe & Fitting Above 2" - Material Handling | 0
A1160 | A1170 | SS | Not Started | Not Started | SEPID-0014 | SEPID-0014 | SEPID-0014.PIP-AGF.CS.AB CS Pipe & Fitting Above 2" | SEPID-0014.PIP-AGF.CS.AB CS Pipe & Fitting Above 2" | CS Pipe & Fitting Above 2" - Material Handling | CS Pipe & Fitting Above 2" - Fit-up | 1
A1170 | A1180 | SS | Not Started | Not Started | SEPID-0014 | SEPID-0014 | SEPID-0014.PIP-AGF.CS.AB CS Pipe & Fitting Above 2" | SEPID-0014.PIP-AGF.CS.AB CS Pipe & Fitting Above 2" | CS Pipe & Fitting Above 2" - Fit-up | CS Pipe & Fitting Above 2" - Welding | 1
A1200 | A1210 | FS | Not Started | Not Started | SEPID-0014 | SEPID-0014 | SEPID-0014.PIP-AGF.SAM.SS SS Pipe & Fitting & Flange | SEPID-0014.PIP-AGF.SAM.SS SS Pipe & Fitting & Flange | SS Pipe & Fitting & Flange Pipe & Fitting - Mobilization | SS Pipe & Fitting & Flange Pipe & Fitting - Material Handling | 0
A1210 | A1220 | SS | Not Started | Not Started | SEPID-0014 | SEPID-0014 | SEPID-0014.PIP-AGF.SAM.SS SS Pipe & Fitting & Flange | SEPID-0014.PIP-AGF.SAM.SS SS Pipe & Fitting & Flange | SS Pipe & Fitting & Flange Pipe & Fitting - Material Handling | SS Pipe & Fitting & Flange Pipe & Fitting - Fit-up | 1
A1220 | A1230 | SS | Not Started | Not Started | SEPID-0014 | SEPID-0014 | SEPID-0014.PIP-AGF.SAM.SS SS Pipe & Fitting & Flange | SEPID-0014.PIP-AGF.SAM.SS SS Pipe & Fitting & Flange | SS Pipe & Fitting & Flange Pipe & Fitting - Fit-up | SS Pipe & Fitting & Flange Pipe & Fitting - Welding | 1
A1250 | A1260 | FS | Not Started | Not Started | SEPID-0014 | SEPID-0014 | SEPID-0014.PIP-AGF.SAM.AS AS Pipe & Fitting & Flange | SEPID-0014.PIP-AGF.SAM.AS AS Pipe & Fitting & Flange | AS Pipe & Fitting - Mobilization | AS Pipe & Fitting - Material Handling | 0
A1260 | A1270 | SS | Not Started | Not Started | SEPID-0014 | SEPID-0014 | SEPID-0014.PIP-AGF.SAM.AS AS Pipe & Fitting & Flange | SEPID-0014.PIP-AGF.SAM.AS AS Pipe & Fitting & Flange | AS Pipe & Fitting - Material Handling | AS Pipe & Fitting - Fit-up | 1
A1270 | A1280 | SS | Not Started | Not Started | SEPID-0014 | SEPID-0014 | SEPID-0014.PIP-AGF.SAM.AS AS Pipe & Fitting & Flange | SEPID-0014.PIP-AGF.SAM.AS AS Pipe & Fitting & Flange | AS Pipe & Fitting - Fit-up | AS Pipe & Fitting - Welding | 1
A1310 | A1320 | FS | Not Started | Not Started | SEPID-0014 | SEPID-0014 | SEPID-0014.PIP-AGF.SAM.MO Monel Pipe & Fitting & Flange | SEPID-0014.PIP-AGF.SAM.MO Monel Pipe & Fitting & Flange | Monel Pipe & Fitting - Mobilization | Monel Pipe & Fitting - Material Handling | 0
A1320 | A1330 | SS | Not Started | Not Started | SEPID-0014 | SEPID-0014 | SEPID-0014.PIP-AGF.SAM.MO Monel Pipe & Fitting & Flange | SEPID-0014.PIP-AGF.SAM.MO Monel Pipe & Fitting & Flange | Monel Pipe & Fitting - Material Handling | Monel Pipe & Fitting - Fit-up | 1
A1330 | A1340 | SS | Not Started | Not Started | SEPID-0014 | SEPID-0014 | SEPID-0014.PIP-AGF.SAM.MO Monel Pipe & Fitting & Flange | SEPID-0014.PIP-AGF.SAM.MO Monel Pipe & Fitting & Flange | Monel Pipe & Fitting - Fit-up | Monel Pipe & Fitting - Welding | 1
A1360 | A1370 | FS | Not Started | Not Started | SEPID-0014 | SEPID-0014 | SEPID-0014.PIP-AGF.GAL.1 GAL Pipe & Fitting & Flange All Size & Thk | SEPID-0014.PIP-AGF.GAL.1 GAL Pipe & Fitting & Flange All Size & Thk | GAL Pipe & Fitting & Flange Mobilization | GAL Pipe & Fitting & Flange Material Handling | 0
A1370 | A1380 | SS | Not Started | Not Started | SEPID-0014 | SEPID-0014 | SEPID-0014.PIP-AGF.GAL.1 GAL Pipe & Fitting & Flange All Size & Thk | SEPID-0014.PIP-AGF.GAL.1 GAL Pipe & Fitting & Flange All Size & Thk | GAL Pipe & Fitting & Flange Material Handling | GAL Pipe & Fitting & Flange Installation & Thread | 1
A1380 | A1390 | SS | Not Started | Not Started | SEPID-0014 | SEPID-0014 | SEPID-0014.PIP-AGF.GAL.1 GAL Pipe & Fitting & Flange All Size & Thk | SEPID-0014.PIP-AGF.GAL.1 GAL Pipe & Fitting & Flange All Size & Thk | GAL Pipe & Fitting & Flange Installation & Thread | GAL Pipe & Fitting & Flange - (QC & QA Report ) | 0
A1400 | A1410 | FS | Not Started | Not Started | SEPID-0014 | SEPID-0014 | SEPID-0014.VAL.INST Valve Installation | SEPID-0014.VAL.INST Valve Installation | Valve Installation - Mobilization | Valve Installation - Handling | 0
A1410 | A1420 | SS | Not Started | Not Started | SEPID-0014 | SEPID-0014 | SEPID-0014.VAL.INST Valve Installation | SEPID-0014.VAL.INST Valve Installation | Valve Installation - Handling | Valve Installation - Installation | 1
A1420 | A1430 | SS | Not Started | Not Started | SEPID-0014 | SEPID-0014 | SEPID-0014.VAL.INST Valve Installation | SEPID-0014.VAL.INST Valve Installation | Valve Installation - Installation | Valve Installation - (QC & QA Report ) | 0
A1440 | A1450 | FS | Not Started | Not Started | SEPID-0014 | SEPID-0014 | SEPID-0014.VAL.SI Special Items Installation | SEPID-0014.VAL.SI Special Items Installation | Special Items - Mobilization | Special Items - Handling | 0
A1450 | A1460 | SS | Not Started | Not Started | SEPID-0014 | SEPID-0014 | SEPID-0014.VAL.SI Special Items Installation | SEPID-0014.VAL.SI Special Items Installation | Special Items - Handling | Special Items - Installation | 1
A1460 | A1470 | SS | Not Started | Not Started | SEPID-0014 | SEPID-0014 | SEPID-0014.VAL.SI Special Items Installation | SEPID-0014.VAL.SI Special Items Installation | Special Items - Installation | Special Items - (QC & QA Report ) | 0
A1480 | A1490 | FS | Not Started | Not Started | SEPID-0014 | SEPID-0014 | SEPID-0014.SUP.NOR Pipe Support Supply ,Fabrication, Erection and Painting | SEPID-0014.SUP.NOR Pipe Support Supply ,Fabrication, Erection and Painting | Pipe Support Mobilization | Pipe Support Material Supply | 0
A1490 | A1500 | SS | Not Started | Not Started | SEPID-0014 | SEPID-0014 | SEPID-0014.SUP.NOR Pipe Support Supply ,Fabrication, Erection and Painting | SEPID-0014.SUP.NOR Pipe Support Supply ,Fabrication, Erection and Painting | Pipe Support Material Supply | Pipe Support Fabrication | 1
A1500 | A1510 | SS | Not Started | Not Started | SEPID-0014 | SEPID-0014 | SEPID-0014.SUP.NOR Pipe Support Supply ,Fabrication, Erection and Painting | SEPID-0014.SUP.NOR Pipe Support Supply ,Fabrication, Erection and Painting | Pipe Support Fabrication | Pipe Support Sandblast & Primer | 7
A1510 | A1520 | SS | Not Started | Not Started | SEPID-0014 | SEPID-0014 | SEPID-0014.SUP.NOR Pipe Support Supply ,Fabrication, Erection and Painting | SEPID-0014.SUP.NOR Pipe Support Supply ,Fabrication, Erection and Painting | Pipe Support Sandblast & Primer | Pipe Support Painting | 7
A1520 | A1530 | SS | Not Started | Not Started | SEPID-0014 | SEPID-0014 | SEPID-0014.SUP.NOR Pipe Support Supply ,Fabrication, Erection and Painting | SEPID-0014.SUP.NOR Pipe Support Supply ,Fabrication, Erection and Painting | Pipe Support Painting | Pipe Support Installation | 7
A1550 | A1560 | FS | Not Started | Not Started | SEPID-0014 | SEPID-0014 | SEPID-0014.SUP.SPL Special Pipe Support (Spring Hanger, Rigid Hanger,…) Erection (Tag Item) | SEPID-0014.SUP.SPL Special Pipe Support (Spring Hanger, Rigid Hanger,…) Erection (Tag Item) | Special Pipe Support Mobilization | Special Pipe Support Material Handling | 0
A1560 | A1570 | SS | Not Started | Not Started | SEPID-0014 | SEPID-0014 | SEPID-0014.SUP.SPL Special Pipe Support (Spring Hanger, Rigid Hanger,…) Erection (Tag Item) | SEPID-0014.SUP.SPL Special Pipe Support (Spring Hanger, Rigid Hanger,…) Erection (Tag Item) | Special Pipe Support Material Handling | Special Pipe Support Installation | 1
A1570 | A1580 | SS | Not Started | Not Started | SEPID-0014 | SEPID-0014 | SEPID-0014.SUP.SPL Special Pipe Support (Spring Hanger, Rigid Hanger,…) Erection (Tag Item) | SEPID-0014.SUP.SPL Special Pipe Support (Spring Hanger, Rigid Hanger,…) Erection (Tag Item) | Special Pipe Support Installation | Special Pipe Support - (QC & QA Report ) | 1
A1590 | A1600 | FS | Not Started | Not Started | SEPID-0014 | SEPID-0014 | SEPID-0014.INS.PNT Painting (Pipe & Fittings) | SEPID-0014.INS.PNT Painting (Pipe & Fittings) | Painting (Pipe & Fittings) Mobilization | Painting (Pipe & Fittings) Surface Preparation (Sand / Grit Blast) | 0
A1600 | A1610 | SS | Not Started | Not Started | SEPID-0014 | SEPID-0014 | SEPID-0014.INS.PNT Painting (Pipe & Fittings) | SEPID-0014.INS.PNT Painting (Pipe & Fittings) | Painting (Pipe & Fittings) Surface Preparation (Sand / Grit Blast) | Painting (Pipe & Fittings) Primer Painting | 7
A1610 | A1620 | FS | Not Started | Not Started | SEPID-0014 | SEPID-0014 | SEPID-0014.INS.PNT Painting (Pipe & Fittings) | SEPID-0014.INS.PNT Painting (Pipe & Fittings) | Painting (Pipe & Fittings) Primer Painting | Painting (Pipe & Fittings) Intermediate Painting | -112
A1620 | A1630 | SS | Not Started | Not Started | SEPID-0014 | SEPID-0014 | SEPID-0014.INS.PNT Painting (Pipe & Fittings) | SEPID-0014.INS.PNT Painting (Pipe & Fittings) | Painting (Pipe & Fittings) Intermediate Painting | Painting (Pipe & Fittings) Top Coat Painting | 7
A1630 | A1640 | SS | Not Started | Not Started | SEPID-0014 | SEPID-0014 | SEPID-0014.INS.PNT Painting (Pipe & Fittings) | SEPID-0014.INS.PNT Painting (Pipe & Fittings) | Painting (Pipe & Fittings) Top Coat Painting | Painting (Pipe & Fittings) Color Coding ,Lettering & Marking | 7
A1640 | A1650 | SS | Not Started | Not Started | SEPID-0014 | SEPID-0014 | SEPID-0014.INS.PNT Painting (Pipe & Fittings) | SEPID-0014.INS.PNT Painting (Pipe & Fittings) | Painting (Pipe & Fittings) Color Coding ,Lettering & Marking | Painting (Pipe & Fittings) Tie Coat Paint layer On Piping | 7
A1650 | A1660 | SS | Not Started | Not Started | SEPID-0014 | SEPID-0014 | SEPID-0014.INS.PNT Painting (Pipe & Fittings) | SEPID-0014.INS.PNT Painting (Pipe & Fittings) | Painting (Pipe & Fittings) Tie Coat Paint layer On Piping | Painting (Pipe & Fittings) Tie Coat Paint layer On Supports | 7
A1680 | A1690 | FS | Not Started | Not Started | SEPID-0014 | SEPID-0014 | SEPID-0014.INS.HOT.PF Insulation Pipe & Fitting | SEPID-0014.INS.HOT.PF Insulation Pipe & Fitting | Insulation Pipe & Fitting Mobilization | Insulation Pipe & Fitting Material Handling | 0
A1690 | A1700 | SS | Not Started | Not Started | SEPID-0014 | SEPID-0014 | SEPID-0014.INS.HOT.PF Insulation Pipe & Fitting | SEPID-0014.INS.HOT.PF Insulation Pipe & Fitting | Insulation Pipe & Fitting Material Handling | Insulation Pipe & Fitting Cutting & Shaping | 0
A1700 | A1710 | SS | Not Started | Not Started | SEPID-0014 | SEPID-0014 | SEPID-0014.INS.HOT.PF Insulation Pipe & Fitting | SEPID-0014.INS.HOT.PF Insulation Pipe & Fitting | Insulation Pipe & Fitting Cutting & Shaping | Insulation Pipe & Fitting Erection Of Insulation | 7
A1710 | A1720 | SS | Not Started | Not Started | SEPID-0014 | SEPID-0014 | SEPID-0014.INS.HOT.PF Insulation Pipe & Fitting | SEPID-0014.INS.HOT.PF Insulation Pipe & Fitting | Insulation Pipe & Fitting Erection Of Insulation | Insulation Pipe & Fitting Sheeting & Sealing | 7
A1700 | A1730 | SS | Not Started | Not Started | SEPID-0014 | SEPID-0014 | SEPID-0014.INS.HOT.PF Insulation Pipe & Fitting | SEPID-0014.INS.HOT.PF Insulation Pipe & Fitting | Insulation Pipe & Fitting Cutting & Shaping | Insulation Pipe & Fitting Sheeting & Sealing - (QC & QA Report ) | 0
A1740 | A1750 | FS | Not Started | Not Started | SEPID-0014 | SEPID-0014 | SEPID-0014.INS.HOT.VA Insulation Valve & Flange (With Box if nesessary) | SEPID-0014.INS.HOT.VA Insulation Valve & Flange (With Box if nesessary) | Insulation Valve & Flange Mobilization | Insulation Valve & Flange Material Handling | 0
A1750 | A1760 | SS | Not Started | Not Started | SEPID-0014 | SEPID-0014 | SEPID-0014.INS.HOT.VA Insulation Valve & Flange (With Box if nesessary) | SEPID-0014.INS.HOT.VA Insulation Valve & Flange (With Box if nesessary) | Insulation Valve & Flange Material Handling | Insulation Valve & Flange Cutting & Shaping | 0
A1760 | A1770 | SS | Not Started | Not Started | SEPID-0014 | SEPID-0014 | SEPID-0014.INS.HOT.VA Insulation Valve & Flange (With Box if nesessary) | SEPID-0014.INS.HOT.VA Insulation Valve & Flange (With Box if nesessary) | Insulation Valve & Flange Cutting & Shaping | Insulation Valve & Flange Erection Of Insulation | 0
A1770 | A1780 | SS | Not Started | Not Started | SEPID-0014 | SEPID-0014 | SEPID-0014.INS.HOT.VA Insulation Valve & Flange (With Box if nesessary) | SEPID-0014.INS.HOT.VA Insulation Valve & Flange (With Box if nesessary) | Insulation Valve & Flange Erection Of Insulation | Insulation Valve & Flange Sheeting & Sealing | 0
A1780 | A1790 | SS | Not Started | Not Started | SEPID-0014 | SEPID-0014 | SEPID-0014.INS.HOT.VA Insulation Valve & Flange (With Box if nesessary) | SEPID-0014.INS.HOT.VA Insulation Valve & Flange (With Box if nesessary) | Insulation Valve & Flange Sheeting & Sealing | Insulation Valve & Flange Sheeting & Sealing - (QC & QA Report ) | 0
A1860 | A1870 | FS | Not Started | Not Started | SEPID-0014 | SEPID-0014 | SEPID-0014.TPC.PWHT Post Weld Heat Treatment - PWHT | SEPID-0014.TPC.PWHT Post Weld Heat Treatment - PWHT | PWHT Mobilization | PWHT | 0
A1870 | A1880 | SS | Not Started | Not Started | SEPID-0014 | SEPID-0014 | SEPID-0014.TPC.PWHT Post Weld Heat Treatment - PWHT | SEPID-0014.TPC.PWHT Post Weld Heat Treatment - PWHT | PWHT | PWHT - (QC & QA Report ) | 0
A1890 | A1900 | SS | Not Started | Not Started | SEPID-0014 | SEPID-0014 | SEPID-0014.TPC.PRE Precommissining of Metalic Piping | SEPID-0014.TPC.PRE Precommissining of Metalic Piping | Preparation of Test Package | Precommissining of Metalic Piping - Mobilization | 0
A1900 | A1910 | FS | Not Started | Not Started | SEPID-0014 | SEPID-0014 | SEPID-0014.TPC.PRE Precommissining of Metalic Piping | SEPID-0014.TPC.PRE Precommissining of Metalic Piping | Precommissining of Metalic Piping - Mobilization | Line Check | 0
A1910 | A1920 | SS | Not Started | Not Started | SEPID-0014 | SEPID-0014 | SEPID-0014.TPC.PRE Precommissining of Metalic Piping | SEPID-0014.TPC.PRE Precommissining of Metalic Piping | Line Check | Hydro Test | 0
A1920 | A1930 | SS | Not Started | Not Started | SEPID-0014 | SEPID-0014 | SEPID-0014.TPC.PRE Precommissining of Metalic Piping | SEPID-0014.TPC.PRE Precommissining of Metalic Piping | Hydro Test | Cleaning & Flushing & Drying | 0
A1930 | A1940 | SS | Not Started | Not Started | SEPID-0014 | SEPID-0014 | SEPID-0014.TPC.PRE Precommissining of Metalic Piping | SEPID-0014.TPC.PRE Precommissining of Metalic Piping | Cleaning & Flushing & Drying | Reinstatement | 0
A1940 | A1950 | SS | Not Started | Not Started | SEPID-0014 | SEPID-0014 | SEPID-0014.TPC.PRE Precommissining of Metalic Piping | SEPID-0014.TPC.PRE Precommissining of Metalic Piping | Reinstatement | Precommissining of Metalic Piping - (QC & QA Report ) | 0
A1960 | A1970 | SS | Not Started | Not Started | SEPID-0014 | SEPID-0014 | SEPID-0014.TPC.CHM Chemical Clearing (Acid & Alkaline) | SEPID-0014.TPC.CHM Chemical Clearing (Acid & Alkaline) | Chemical Clearing (Acid & Alkaline) Mobilization | Chemical Clearing (Acid & Alkaline) Material Supply | 0
A1970 | A1980 | SS | Not Started | Not Started | SEPID-0014 | SEPID-0014 | SEPID-0014.TPC.CHM Chemical Clearing (Acid & Alkaline) | SEPID-0014.TPC.CHM Chemical Clearing (Acid & Alkaline) | Chemical Clearing (Acid & Alkaline) Material Supply | Chemical Clearing (Acid & Alkaline) | 0
A1980 | A1990 | SS | Not Started | Not Started | SEPID-0014 | SEPID-0014 | SEPID-0014.TPC.CHM Chemical Clearing (Acid & Alkaline) | SEPID-0014.TPC.CHM Chemical Clearing (Acid & Alkaline) | Chemical Clearing (Acid & Alkaline) | Chemical Clearing (Acid & Alkaline) - (QC & QA Report ) | 0
A2000 | A2010 | SS | Not Started | Not Started | SEPID-0014 | SEPID-0014 | SEPID-0014.TPC.PMI P.M.I | SEPID-0014.TPC.PMI P.M.I | P.M.I - Mobilization | P.M.I | 0
A2010 | A2020 | SS | Not Started | Not Started | SEPID-0014 | SEPID-0014 | SEPID-0014.TPC.PMI P.M.I | SEPID-0014.TPC.PMI P.M.I | P.M.I | P.M.I - (QC & QA Report ) | 0
A1120 | A1140 | SS | Not Started | Not Started | SEPID-0014 | SEPID-0014 | SEPID-0014.PIP-AGF.CS.UN CS Pipe & Fitting Under 2" | SEPID-0014.PIP-AGF.CS.UN CS Pipe & Fitting Under 2" | CS Pipe & Fitting Under 2" - Fit-up | CS Pipe & Fitting Under 2" - (QC & QA Report ) | 0
A1170 | A1190 | SS | Not Started | Not Started | SEPID-0014 | SEPID-0014 | SEPID-0014.PIP-AGF.CS.AB CS Pipe & Fitting Above 2" | SEPID-0014.PIP-AGF.CS.AB CS Pipe & Fitting Above 2" | CS Pipe & Fitting Above 2" - Fit-up | CS Pipe & Fitting Above 2" - (QC & QA Report ) | 0
A1220 | A1240 | SS | Not Started | Not Started | SEPID-0014 | SEPID-0014 | SEPID-0014.PIP-AGF.SAM.SS SS Pipe & Fitting & Flange | SEPID-0014.PIP-AGF.SAM.SS SS Pipe & Fitting & Flange | SS Pipe & Fitting & Flange Pipe & Fitting - Fit-up | SS Pipe & Fitting & Flange Pipe & Fitting - (QC & QA Report ) | 0
A1270 | A1290 | SS | Not Started | Not Started | SEPID-0014 | SEPID-0014 | SEPID-0014.PIP-AGF.SAM.AS AS Pipe & Fitting & Flange | SEPID-0014.PIP-AGF.SAM.AS AS Pipe & Fitting & Flange | AS Pipe & Fitting - Fit-up | AS Pipe & Fitting - (QC & QA Report ) | 0
A1330 | A1350 | SS | Not Started | Not Started | SEPID-0014 | SEPID-0014 | SEPID-0014.PIP-AGF.SAM.MO Monel Pipe & Fitting & Flange | SEPID-0014.PIP-AGF.SAM.MO Monel Pipe & Fitting & Flange | Monel Pipe & Fitting - Fit-up | Monel Pipe & Fitting - (QC & QA Report ) | 0
A1500 | A1540 | SS | Not Started | Not Started | SEPID-0014 | SEPID-0014 | SEPID-0014.SUP.NOR Pipe Support Supply ,Fabrication, Erection and Painting | SEPID-0014.SUP.NOR Pipe Support Supply ,Fabrication, Erection and Painting | Pipe Support Fabrication | Pipe Support - (QC & QA Report ) | 0
A1600 | A1670 | SS | Not Started | Not Started | SEPID-0014 | SEPID-0014 | SEPID-0014.INS.PNT Painting (Pipe & Fittings) | SEPID-0014.INS.PNT Painting (Pipe & Fittings) | Painting (Pipe & Fittings) Surface Preparation (Sand / Grit Blast) | Painting (Pipe & Fittings) - (QC & QA Report ) | 0
A2041 | A1150 | FS | Not Started | Not Started | SEPID-0014 | SEPID-0014 | SEPID-0014.Ml Mileston Important | SEPID-0014.PIP-AGF.CS.AB CS Pipe & Fitting Above 2" | Project Kickoff Meeting | CS Pipe & Fitting Above 2" - Mobilization | 0
A2041 | A1100 | FS | Not Started | Not Started | SEPID-0014 | SEPID-0014 | SEPID-0014.Ml Mileston Important | SEPID-0014.PIP-AGF.CS.UN CS Pipe & Fitting Under 2" | Project Kickoff Meeting | CS Pipe & Fitting Under 2" - Mobilization | 224
A2041 | A1200 | FS | Not Started | Not Started | SEPID-0014 | SEPID-0014 | SEPID-0014.Ml Mileston Important | SEPID-0014.PIP-AGF.SAM.SS SS Pipe & Fitting & Flange | Project Kickoff Meeting | SS Pipe & Fitting & Flange Pipe & Fitting - Mobilization | 98
A2041 | A1250 | FS | Not Started | Not Started | SEPID-0014 | SEPID-0014 | SEPID-0014.Ml Mileston Important | SEPID-0014.PIP-AGF.SAM.AS AS Pipe & Fitting & Flange | Project Kickoff Meeting | AS Pipe & Fitting - Mobilization | 70
A2041 | A1310 | FS | Not Started | Not Started | SEPID-0014 | SEPID-0014 | SEPID-0014.Ml Mileston Important | SEPID-0014.PIP-AGF.SAM.MO Monel Pipe & Fitting & Flange | Project Kickoff Meeting | Monel Pipe & Fitting - Mobilization | 336
A2041 | A1360 | FS | Not Started | Not Started | SEPID-0014 | SEPID-0014 | SEPID-0014.Ml Mileston Important | SEPID-0014.PIP-AGF.GAL.1 GAL Pipe & Fitting & Flange All Size & Thk | Project Kickoff Meeting | GAL Pipe & Fitting & Flange Mobilization | 203
A1490 | A2000 | SS | Not Started | Not Started | SEPID-0014 | SEPID-0014 | SEPID-0014.SUP.NOR Pipe Support Supply ,Fabrication, Erection and Painting | SEPID-0014.TPC.PMI P.M.I | Pipe Support Material Supply | P.M.I - Mobilization | 0
A1180 | A1400 | SS | Not Started | Not Started | SEPID-0014 | SEPID-0014 | SEPID-0014.PIP-AGF.CS.AB CS Pipe & Fitting Above 2" | SEPID-0014.VAL.INST Valve Installation | CS Pipe & Fitting Above 2" - Welding | Valve Installation - Mobilization | 224

## USERDATA
user_data
UserSettings Do Not Edit
DurationQtyType=QT_Day ShowAsPercentage=0 SmallScaleQtyType=QT_Hour DateFormat=M/d/yyyy CurrencyFormat=US Dollar